## Slide 1: ADESE_Presentation
Challenges, findings, opportunities & lessons learned during project implementation

## Slide 2: The following were the challenges encountered during project implementation
We had passed through a challenge of late receipt of fund from Trees for the Future. To overcome this we did the following;-
During the waiting period, we started working with activities that did not require cash, such as nursery daily activities.
Also we built a good relationship with Vendors that makes it easier for us to take goods and services from them on credit terms.

## Slide 3: Oppoturnities
We developed good relationships with Vendors which led to take goods and services on credit
To be Known by the Government and other Institutions.
We planted and distributed trees around Sindiga District.

## Slide 4: Lesson Leaned
We should have tolerance
If farmers will be trained on the benefit of environmental conservation, they do better.

## Slide 5: Plans for next season
The project aims to serve a total of 155 farmers, including 81 male farmers and 31 female farmers in Mungaa, 20 male farmers and 10 female farmers in Isuna, and 12 male farmers and 1 female farmer in Kisaki.
To establish 155 forest gardens
number of trees to be raised to the season of 2023/2024 is 280,550 this includes the following tree species:
Acacia polycantha: 195,300 trees for live fencing purposes.
Avocado: 775 trees for fruit production.
Passion fruit: 775 trees for fruit production.
Grilicidia sepium: 83,700 trees for live fencing.